## Project Planner
McDonnell Thesis - Gantt Chart |  |  |  |  | Period Highlight: | 13 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLANNED START | PLANNED DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245
[6 empty] | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 30/05 | 31/05 | 01/06 | 02/06 | 03/06 | 04/06 | 05/06 | 06/06 | 07/06 | 08/06 | 09/06 | 10/06 | 11/06 | 12/06 | 13/06 | 14/06 | 15/06 | 16/06 | 17/06 | 18/06 | 19/06 | 20/06 | 21/06 | 22/06 | 23/06 | 24/06 | 25/06 | 26/06 | 27/06 | 28/06 | 29/06 | 30/06 | 01/07 | 02/07 | 03/07 | 04/07 | 05/07 | 06/07 | 07/07 | 08/07 | 09/07 | 10/07 | 11/07 | 12/07 | 13/07 | 14/07 | 15/07 | 16/07 | 17/07 | 18/07 | 19/07 | 20/07 | 21/07 | 22/07 | 23/07 | 24/07 | 25/07 | 26/07 | 27/07 | 28/07 | 29/07 | 30/07 | 31/07 | 01/08 | 02/08 | 03/08 | 04/08 | 05/08 | 06/08 | 07/08 | 08/08 | 09/08 | 10/08 | 11/08 | 12/08 | 13/08 | 14/08 | 15/08 | 16/08 | 17/08 | 18/08 | 19/08 | 20/08 | 21/08 | 22/08 | 23/08 | 24/08 | 25/08 | 26/08 | 27/08 | 28/08 | 29/08 | 30/08 | 31/08 | 01/09 | 02/09 | 03/09 | 04/09 | 05/09 | 06/09 | 07/09 | 08/09 | 09/09 | 10/09 | 11/09 | 12/09 | 13/09 | 14/09 | 15/09 | 16/09 | 17/09 | 18/09 | 19/09 | 20/09 | 21/09 | 22/09 | 23/09 | 24/09 | 25/09 | 26/09 | 27/09 | 28/09 | 29/09 | 30/09 | 01/10 | 02/10 | 03/10 | 04/10 | 05/10 | 06/10 | 07/10 | 08/10 | 09/10 | 10/10 | 11/10 | 12/10 | 13/10 | 14/10 | 15/10 | 16/10 | 17/10 | 18/10 | 19/10 | 20/10 | 21/10 | 22/10 | 23/10 | 24/10 | 25/10 | 26/10 | 27/10
BACKGROUND AND RESEARCH | 1 | 9 | 1 | 12 | 100%
Background: Problem space investigation | 1 | 1 | 1 | 2 | 100%
Background: Thesis focus | 2 | 1 | 2 | 2 | 100%
Background: Scoping | 3 | 1 | 3 | 1 | 100%
Background: Literature review | 3 | 3 | 3 | 4 | 100%
Background: Literature review round 2 | 8 | 3 | 8 | 3 | 0%
SIMULATION | 2 | 6 | 3 | 4 | 83.33%
Engine comparison | 2 | 1 | 3 | 1 | 0%
Inter Process communications reesarch and prototype | 8 | 3 | 8 | 2 | 100%
Time dilation research and prototype | 11 | 2 | 11 | 1 | 100%
COMPUTER VISION | 3 | 12 | 3 | 14 | 58.33%
Python vs C++ research | 3 | 1 | 3 | 1 | 100%
Digital Image Processing course | 3 | 4 | 3 | 5 | 100%
MATLAB tests | 5 | 2 | 5 | 2 | 100%
Python famil | 4 | 2 | 4 | 3 | 0%
Open CV famil | 7 | 3 | 6 | 3 | 0%
LANE DETECTION | 7 | 9 | 7 | 3 | 57.14%
Background research | 7 | 3 | 7 | 2 | 100%
Straight lane tests | 9 | 1 | 8 | 1 | 100%
Curved lane option research | 11 | 3 |  |  | 0%
Curved lane tests | 14 | 2 |  |  | 0%
0%
0%
0%
GPS CURVE MATCHING | 3 | 7 | 3 | 7 | 40%
GPS data analysis | 3 | 1 | 3 | 1 | 100%
Curve matching option research | 10 | 6 | 8 | 6 | 30%
0%
0%
0%
0%
MISC | 11 | 10 | 11 | 3 | 60%
Interim report | 11 | 2 | 11 | 2 | 100%
Viva preparation | 12 | 1 | 12 | 1 | 100%
Draft summary report | 32 | 2 |  |  | 0%
Final Seminar preparation | 32 | 3 |  |  | 0%
Final summary report | 34 | 2 |  |  | 0%
Distributable package of simulation | 30 | 4 |  |  | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%